## Milestones
Phase | Week | Workstream | Module | Task | Priority | EffortHours | OwnerRole | Dependencies | DefinitionOfDone | TargetStart | TargetEnd | Status | Milestone | CommercialImpact
Phase 0 | 1 | Platform Stability | Backend Runtime | Fix backend start:dev and standardize env/start scripts | P0 | 10 | Fullstack Dev | Current backend config | Backend runs on port 3000 reliably for 3 consecutive restarts | 2026-02-24 | 2026-03-02 | Planned | M0 Runtime stable | Required for demos and onboarding
Phase 0 | 1 | Platform Stability | Observability | Add startup health checks and error logging baseline | P0 | 4 | Backend Dev | Backend runtime stable | /health and structured startup errors available | 2026-02-24 | 2026-03-02 | Planned | M0 Runtime stable | Reduces support risk during pilots
Phase 0 | 1 | Core Finance QA | Deposits/Withdrawals | Complete smoke suite for all payment types and reversals | P0 | 8 | QA + Fullstack | Latest deposits fixes | 20/20 high-value tests pass | 2026-02-24 | 2026-03-02 | Planned | M1 Cashflow hardened | Protects accounting trust
Phase 1 | 2 | Security & Access | Users & Roles | Implement user profiles and role CRUD | P0 | 12 | Fullstack Dev | Runtime stable | Admin can create/edit/disable users and assign roles | 2026-03-03 | 2026-03-09 | Planned | M2 Access foundation | Needed for multi-SACCO sale readiness
Phase 1 | 2 | Security & Access | Permissions | Implement permission matrix per module/action | P0 | 12 | Backend Dev | Users & Roles | Unauthorized actions blocked server-side and hidden client-side | 2026-03-03 | 2026-03-09 | Planned | M2 Access foundation | Enterprise requirement
Phase 1 | 3 | Approvals | Maker-Checker | Add configurable approvals for high-risk actions | P0 | 14 | Fullstack Dev | Permissions | Pending/approved/rejected workflow with audit trail | 2026-03-10 | 2026-03-16 | Planned | M3 Governance controls | Compliance + controls
Phase 1 | 3 | Audit | Audit Trail | Immutable audit entries for settings and financial actions | P0 | 8 | Backend Dev | Maker-Checker | All critical actions include actor, before/after, timestamp | 2026-03-10 | 2026-03-16 | Planned | M3 Governance controls | Critical in due diligence
Phase 2 | 4 | Assets Lifecycle | Asset Purchases | Create asset purchase posting flow with capitalization | P1 | 12 | Fullstack Dev | Permissions + audit | Purchase posts correctly to asset and cash/bank accounts | 2026-03-17 | 2026-03-23 | Planned | M4 Asset purchases live | Expands product scope
Phase 2 | 4 | Assets Lifecycle | Depreciation | Automate depreciation schedules and monthly posting | P1 | 10 | Backend Dev | Asset purchases | Depreciation run generates expected journal entries | 2026-03-17 | 2026-03-23 | Planned | M4 Asset purchases live | Improves reporting quality
Phase 2 | 5 | Assets Lifecycle | Asset Disposal/Sale | Implement sale/disposal with gain/loss accounting | P1 | 12 | Fullstack Dev | Asset purchases + depreciation | Disposal updates register and posts gain/loss | 2026-03-24 | 2026-03-30 | Planned | M5 Asset lifecycle complete | Strong differentiator for SACCOs
Phase 2 | 5 | Configuration | Settings Governance | Settings versioning + change approvals + effective dates | P1 | 8 | Backend Dev | Audit trail | Settings changes tracked and reversible | 2026-03-24 | 2026-03-30 | Planned | M5 Asset lifecycle complete | Safer operations
Phase 3 | 6 | Multi-SACCO | Tenant Isolation | Harden data isolation and tenancy boundaries | P0 | 14 | Backend Dev | User access model | No cross-tenant reads/writes in critical endpoints | 2026-03-31 | 2026-04-06 | Planned | M6 Multi-SACCO hardening | Mandatory for commercialization
Phase 3 | 6 | Multi-SACCO | Tenant Provisioning | Onboard new SACCO wizard + default charts/settings | P1 | 10 | Fullstack Dev | Tenant isolation | New SACCO can be provisioned in under 15 minutes | 2026-03-31 | 2026-04-06 | Planned | M6 Multi-SACCO hardening | Accelerates sales onboarding
Phase 3 | 7 | Branding | White-label | Per-SACCO branding (logo/colors/legal docs) | P2 | 8 | Frontend Dev | Tenant model | Branding applies cleanly by tenant | 2026-04-07 | 2026-04-13 | Planned | M7 Sellable product pack | Supports resale strategy
Phase 3 | 7 | Commercial | Packaging | Define pricing tiers + feature flags per plan | P1 | 8 | Product + Dev | Tenant provisioning | Feature availability configurable by plan | 2026-04-07 | 2026-04-13 | Planned | M7 Sellable product pack | Revenue readiness
Phase 4 | 8 | Reporting | Financial Reports | Finalize BS/IS/TB reconciliation packs and exports | P0 | 10 | Finance QA + Dev | Core modules stable | Month-end pack ties out with zero unexplained variance | 2026-04-14 | 2026-04-20 | Planned | M8 Reporting confidence | Client trust and auditability
Phase 4 | 8 | Reporting | Management Dashboards | Operational KPI dashboards for SACCO leadership | P2 | 8 | Frontend Dev | Reporting data quality | KPI cards and trends validated | 2026-04-14 | 2026-04-20 | Planned | M8 Reporting confidence | Executive visibility
Phase 4 | 9 | Integrations | Bank/MPESA Imports | Import and reconcile bank + mobile money statements | P1 | 12 | Fullstack Dev | Tenant + permissions | Import parser + reconciliation workflow complete | 2026-04-21 | 2026-04-27 | Planned | M9 Integration layer | Reduces manual work
Phase 4 | 9 | Integrations | Notifications | Email/SMS notifications for approvals and arrears | P2 | 8 | Backend Dev | Approvals | Templates + send logs + retries | 2026-04-21 | 2026-04-27 | Planned | M9 Integration layer | Improves collections
Phase 5 | 10 | Quality | UAT + Regression | Run UAT scripts across all core modules | P0 | 12 | QA + Product | All prior milestones | UAT pass rate >= 95% with no open P0 | 2026-04-28 | 2026-05-04 | Planned | M10 Release candidate | Go-live readiness
Phase 5 | 10 | Operations | Go-live Playbook | Deploy, backup/restore drill, incident playbook | P0 | 8 | DevOps + Lead | UAT complete | Runbook approved and restore tested | 2026-04-28 | 2026-05-04 | Planned | M10 Release candidate | Operational confidence
Phase 5 | 10 | Commercial | Sales Enablement | Create demo script, one-pager, implementation checklist | P1 | 6 | Product + Lead | Stable release candidate | Reusable sales/demo assets ready | 2026-04-28 | 2026-05-04 | Planned | M10 Release candidate | Supports client acquisition

## Summary
Metric | Value
Schedule Duration (weeks) | 10
Part-time Capacity (hrs/week) | 12-15
Total Planned Effort (hrs) | 214
P0 Items | 11
P1 Items | 8
P2 Items | 3
Commercial Milestone | Multi-SACCO hardened + sales pack